## Slide 1: Quincy Mine Hoist Association
04/27/2020
Boiler House #5 & Machine Shop Restoration
Midwest Structural Builds
Cole LeBarre Logan Stein Mason Chapman Wyatt Brown
1

## Slide 2: Overview
Project Outline
Site Visit
Design Process
Construction Schedule
Cost Analysis
Next Steps
Summary
Questions
Logan Stein
04/27/2020
2

## Slide 3: Project Outline
Work with Quincy Mine Hoist Association
Vision: Preserve Quincy Mine’s historical resources
Solution: Renovate Boiler House #5 & Machine Shop
Restore both buildings to be historically accurate
  Keeping overall cost and timeline in mind
Wyatt Brown
04/27/2020
3

## Slide 4: Project Location
4
Cole LeBarre

## Slide 5: Site Visit
First Site Visit
  Learn how to access site
  Cleared snow
  Created list of items to restore
  Initial Measurements of Building
Second Site Visit
  Continued measurements
  Pictures of trusses/building
  Trestle measurements
5
Cole LeBarre

## Slide 6: Design Process - Concept
Cost Saving with Historic Accuracy
  Ability to save money by using modern technology
  Ability to obtain material quicker
Maintain historical accuracy
Machine Shop
  Concrete and Wood Planks
Wyatt Brown
04/27/2020
6

## Slide 7: Design - Trestle
#
Total Span = 54’
Total Load per section = 5800 #
AWC - NDS for Wood Construction
  Total Section Cap. = 170,000
Allows Cart use
7
Logan Stein

## Slide 8: Design - Trestle Footings
18” wide
18” exposed above ground
60” underground
  12” past frost line
Footing Capacity = 970,000 #
Sandy-Gravel = 30,000 #
  Governs load
8
Logan Stein

## Slide 9: Design - Truss Analysis
Loading
  ATC Hazards by location
  Dead+Snow+Wind governs
Steel Code
  RISA3D checks steel code
  All steel is up to code specs
  Truss resists all loading eﬀectively to continue with roof replacement.
9
Cole LeBarre

## Slide 10: Design - Roof System
Stringers
  2”x8”x12’
Steel Rooﬁng
  Match Machine Shop as closely as possible
  Was originally a tin roof
10
Cole LeBarre

## Slide 11: Design - Machine Shop Floor
American Wood Council Span Calculator
GPI 40 wood joist
  16” on center
  16’ span with 40 psf LL + 10 psf DL
  Allows for static displays of machinery
2” x 6” x 12’ decking
Logan Stein

## Slide 12: Construction Schedule
Best route for construction is in phases
  Four phases in total
  Tentatively scheduled a year apart: Start Spring 2021- Finish late Spring 2024
  Designed to hold tour in prime Summer months
Order of phases based on importance and structural integrity
  Follows typical construction (Permits → Clearing → Concrete)
Mason Chapman

## Slide 13: Cost Analysis
Total cost is about $385,000 with a 10% contingency.
This includes all material, equipment
and labor throughout the phases of this project
All estimates are maximum as some material can be reused
Phase 1: | $25,000
Phase 2: | $45,000
Phase 3: | $70,000
Phase 4: | $140,000
Contingency- 10%: | $28,000
Overhead & Profit | $77,000
Total: | $385,000
Wyatt Brown

## Slide 14: Cost Analysis- Phase 1
Roof- Wood stringers on top of trusses and a pro-rib style steel sheet
Phase 1: | 
Roof: | $25,000
Total: | $25,000
Wyatt Brown

## Slide 15: Cost Analysis- Phase 2
Site Work- Clearing debris, shrubs and trees
Concrete Slabs- Both rooms in the
Boiler Plant and in the Machine Shop
Phase 2: | 
Site Work: | $5,000
Concrete Slabs: | $40,000
Total: | $45,000
Wyatt Brown

## Slide 16: Cost Analysis- Phase 3
Doors- Two custom doors in the front and side of building
Steel Replacement- Replacing rusted
out steel under the rail system
Windows- Replacing damaged frames with complete windows
Phase 3: | 
Doors: | $1,500
Steel Replacement: | $3,500
Windows: | $65,000
Total: | $70,000
Wyatt Brown

## Slide 17: Cost Analysis- Phase 4
Brick Work- Demolish boiler walls and use those bricks for rebuild
Windows- Replacing remaining
damaged frames with complete windows
Miscellaneous Allowance
Machine Shop- Floor System
Trestle- Full restoration of the railroad trestles on the front of the building
Phase 4: | 
Brick Work: | $51,000
Windows: | $50,000
Allowance: | $7,500
Machine Shop: | $11,000
Trestle: | $20,500
Total: | $140,000
Wyatt Brown

## Slide 18: Next Steps
Obtain funding
Work with a licensed engineer
Get needed permits
Determine winterizing and maintenance schedule
Start construction
Mason Chapman

## Slide 19: Summary
Project Outline
  Renovate Boiler House & Machine Shop
Site Visit
  Created list of items to renovate & took initial measurements
Design Process
  Structurally sound and historically accurate
Construction Schedule
  Four phases starting spring 2021
Cost Analysis
  Total cost of approx. $385,000
Next Steps
  Funding, engineer, permit, etc.
Mason Chapman

## Slide 20: Acknowledgements
David Nelson
Dr. Theresa Ahlborn
Glenda Bierman
George Kiiskila
Logan Stein
04/27/2020
20

## Slide 21: Questions
21